## Instructions
		Using the Status tracker

At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
	If 5 team members each spent an hour, that counts as 5 hours
	Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)

For new activities, identify the type of activity - documentation, coordination, estimation etc.

At the end of each week, plan ahead for the following week
	Identify people responsible for each activity
	Estimate the hours needed for the activity

PROJECT NUMBER	23
PROJECT NAME	PORTFOLIO MANAGEMENT OF STARTUP INVESTEMENTS
PROJECT MENTOR (sponsor)	Anirudh Govindarajan
TEAM MEMBERS	Prakhar
	Ashish
	Chirag
	Sohan

## Status
PROJECT NUMBER	23
PROJECT NAME	PORTFOLIO MANAGEMENT OF STARTUP INVESTMENTS
PROJECT MENTOR (sponsor)	Anirudh Govindarajan

Activity Name	Type	Responsible	Estimated Team Hours	Actual Hours	Status	Comments	Estimation error	Estimation error %
See Instructions sheet for usage
Week 1 (January 16- January 21)
Fix meeting with client	Coordination	TA	0.75	0.75	Done	We were introduced to the client via a google meet . In this meet all the 3 teams interacted with the client and were given instructions about NDA signing.	0	0
GIT Repository setup	Preparation	Mentor	0.25	0.25	Done	Since we are under a NDA we cannot submit code in repo created by college , so client created company’s repositry and all members were invited to it	0	0
Client meeting	Coordination	All	2	2	Done	All the 3 teams in the venture vault met in the CIE and were given the complete introduction about the company and the impact we will be creating	0	0
Research existing technology	Preparation	All	2.5	3	Done	In this time period we were given some sources about various investing firms and how the market of investing works. We also learned about git that will be used througout the project. All of this communication was taking place through slack.	-0.5	16.6666666666667
Project synopsis writeup	Documentation	All	2.5	2	Done	This was a course requirement that we were supposed to do in which we were to explain what our project is	0.5	25
Client Meeting MOM	Documentation	Chirag,Prakhar	0.5	0.5	Done	A MoM for the 1st mega meet was created and was submitted in the github repo of the college.	0	0
Team Meeting	Coordination	All	1	0.5	Done	A team meeting was held in bakul so that we can decide how to work througout the project, This team meet helped us to know each others strengths and how division of work will be done such that it is equal and fair througout the project.	0.5	100
Status tracker	Documentation	Sohan,Ashish	0.5	0.5	Done	Status tracker was updated for the work done till now.	0	0
Week 2 (January 22 - January 28)
Client meeting	Coordination	All	2	2	Done	In this client meet we were told the milestones of the company and also technologies were listed which will be used to build the product	0	0
Client Meeting MOM	Documentation	Ashish,sohan	0.5	0.5	Done	MoM for the previous meet was documented	0	0
Status tracker	Documentation	Ashish,Prakhar	0.5	0.5	Done	Status tracker was updated for the work done till now.	0	0
Project Plan	Documentation	Chirag,Sohan	1.5	2	Done	Documentation of project plan started whose deadline is on 31st Jan	-0.5	25
Research on Current Market for Our project	Preparation	All	1.5	2	Done	Checking the current competitive products	-0.5	25
Week 3 (January 29 - February 4)
Client meeting	Coordination	All	1	1.25	Done	In this client meet we were introduced with the concept of SOP and its importance in a company, our team was given the task to draft the SOP of the company which will be a rulebook who everyone in the company has to abide to	-0.25	20
Client Meeting MOM	Documentation	Prakhar,Sohan	0.5	0.5	Done	MoM for the previous meet was documented	0	0
Collection of resources	Preparation	All	5	3.75	Done	Resource collection i.e. data dump was created and references from various other companies were collected and dumped to a google doc of company	1.25	33.3333333333333
Status tracker	Documentation	Chirag,Ashish	0.5	0.5	Done	Status tracker was updated for the work done till now.	0	0
Week(Febraury 5-11)
Client meeting	Coordination	All	1	1	Done	After the resources were collected , in this meet client gave us the task to extract information from these referrences that will help us to build the building blocks for our company	0	0
Client Meeting MOM	Documentation	Prakhar,chirag	0.5	0.5	Done	MoM for the previous meet was documented	0	0
Extraction For building SOP	Preparation	All	2.5	4	Done	All the team members sat and read through all the references to extract relevant information about the SOP’s	-1.5	37.5
Version1 of SOP	Documentation	Prakhar,Chirag,Sohan	3	4	Done	Version 1 of the SOP was documented	-1	25
Version2 of SOP	Documentation	All	2	1.5	Done	After the 1st Version of SOP a iteration was made and it was refined and 2nd Version of SOP was created	0.5	33.3333333333333
Status tracker	Documentation	Ashish,	0.5	0.5	Done	Status tracker was updated for the work done till now.	0	0
Week 5(Febrauary 12-18)
Client meeting	Coordination	All	2	2	Done	A 2nd Mega meet was held in CIE with all the employees of venture vault met and showed their work to each tem ,we were asked to make a final iteration on the SOP and publish it to company’s github	0	0
Client Meeting MOM	Documentation	Ashish,Sohan	0.5	0.5	Done	MoM for the previous meet was documented	0	0
Final SOP	Preparation	All	1.5	2.5	Done	Final SOP was released and pushed on company’s github and was made public to all the teams of venture vault	-1	40
Finalise SRS Document	Documentation	Chirag,	3	5	Done	SRS document that was a course requirement was documented	-2	40
Research on Tech Workflow of Portfolio Tracking	Preparation	All	3	2	Done	We were now explained the 1st basic feature for the MVP i.e. portfolio managment and were asked to research about it	1	50
Drafting on Tech Workflow of Portfolio Tracking (version 1)	Documentation	All	2	3	Done	An informal doc was created to write basic workflow for the 1st Feature	-1	33.3333333333333
Status tracker	Documentation	Ashish,Sohan	0.5	0.5	Done	Status tracker was updated for the work done till now.	0	0
Week 6 (Feburary 19-25)
Client meeting	Coordination	All	1	1.75	Done	We as a team explained the workflow of the document , and we were asked to formalize it and to find the technlogies that will be used	-0.75	42.8571428571429
2nd Version of tech Workflow of portfolio tracking	Documentation	All	2	2	Done	Technologies that will be used were listed and also workflow was listed for each feature	0	0
Client meeting	Coordination	All	1	1.5	Done	Doubts regarding workflow were cleared and brainstorming was done to get rid of ambiguitites	-0.5	33.3333333333333
3rd Version of tech Workflow of portfolio tracking	Documentation	All	2	2.5	Done	Workflow refinement	-0.5	20
Client meeting	Coordination	All	1	1.5	Done	Workflow was confirmed and we were given task of adding visual aids , finding cost that will be incurred etc	-0.5	33.3333333333333
Final Workflow	Documentation	All	3	6	Done	Brainstorming on the final workflow is being conducted and costing is also being find out. Meanwhile a UI/UX designer was hired to aid in designing the UI of company	-3	50
Test Tracker Document	Documentation	Chirag	2	3.5	Done	Test cases were designed according to the use cases specified in the SRS document	-1.5	42.8571428571429
Status tracker	Documentation	Chirag,	0.5	0.5	Done	Status tracker was updated for the work done till now.	0	0