## Instructions
		Using the Status tracker

At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
	If 5 team members each spent an hour, that counts as 5 hours
	Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)

For new activities, identify the type of activity - documentation, coordination, estimation etc.

At the end of each week, plan ahead for the following week
	Identify people responsible for each activity
	Estimate the hours needed for the activity

PROJECT NUMBER	23
PROJECT NAME	PORTFOLIO MANAGEMENT OF STARTUP INVESTEMENTS
PROJECT MENTOR (sponsor)	Anirudh Govindarajan
TEAM MEMBERS	Prakhar
	Ashish
	Chirag
	Sohan

## Status
PROJECT NUMBER	23
PROJECT NAME	PORTFOLIO MANAGEMENT OF STARTUP INVESTMENTS
PROJECT MENTOR (sponsor)	Anirudh Govindarajan

Activity Name	Type	Responsible	Estimated Team Hours	Actual Hours	Status	Comments	Estimation error	Estimation error %
See Instructions sheet for usage
Week 1 (January 16- January 21)
Fix meeting with client	Coordination	TA	0.5	0.5	Done		0	0
GIT Repository setup	Preparation	Mentor	1	1	Done		0	0
Client meeting	Coordination	All	2	2	Done	Make sure scoping questions are included	0	0
Research existing technology	Preparation	All	3	2	Done		1	50
Project synopsis writeup	Documentation	All	2.5	2	Done		0.5	25
Client Meeting MOM	Documentation	Chirag,Prakhar	0.5	0.5	Done		0	0
Team Meeting	Coordination	All	1	0.5	Done		0.5	100
Status tracker	Documentation	Sohan,Ashish	0.5	0.5	Done		0	0
Week 2 (January 22 - January 28)
Client meeting	Coordination	All	2	2	Done	Make sure scoping questions are included	0	0
Client Meeting MOM	Documentation	Ashish,sohan	0.5	0.5	Done		0	0
Status tracker	Documentation	Ashish,Prakhar	0.5	0.5	Done		0	0
Project Plan	Documentation	Chirag,Sohan	1.5	2	Done		-0.5	25
Research on Current Market for Our project	Preparation	All	1.5	2	Done		-0.5	25
Week 3 (January 29 - February 4)
Client meeting	Coordination	All	0.75	0.75	Done		0	0
Client Meeting MOM	Documentation	Prakhar,Sohan	0.5	0.5	Done		0	0
Collection of resources	Preparation	All	5	3.75	Done		1.25	33.3333333333333
Status tracker	Documentation	Chirag,Ashish	0.5	0.5	Done		0	0
Week(Febraury 5-11)
Client meeting	Coordination	All	0.5	0.5	Done		0	0
Client Meeting MOM	Documentation	Prakhar,chirag	0.5	0.5	Done		0	0
Extraction For building SOP	Preparation	All	2.5	3	Done		-0.5	16.6666666666667
Version1 of SOP	Documentation	Prakhar,Chirag,Sohan	3.5	3	Done		0.5	16.6666666666667
Version2 of SOP	Documentation	All	1	1.5	Done		-0.5	33.3333333333333
Status tracker	Documentation	Ashish,	0.5	0.5	Done		0	0
Week 5(Febrauary 12-18)
Client meeting	Coordination	All	1	1	Done		0	0
Client Meeting MOM	Documentation	Ashish,Sohan	0.5	0.5	Pending		0	0
Version3 of SOP	Preparation	All	1	1	Done		0	0
Finalise SRS Document	Documentation	Chirag,	3	5	Done		-2	40
Research on Tech Workflow of Portfolio Tracking	Preparation	Prakhar,	3.5	2.5	Done		1	40
Drafting on Tech Workflow of Portfolio Tracking (version 1)	Documentation	All	2	3	Done		-1	33.3333333333333
Status tracker	Documentation	Ashish,Sohan	0.5	0.5	Done		0	0
Week 6